# CE Activity Timeline-Deliverables

## PRE ACTIVITY

| Responsibility | Task | Due Date |
| --- | --- | --- |
| Planning Committee | Submit online CE Event Form. | 40 days prior |
| Planning Committee /Speaker(s) | Submit online Activity Application (incl. Speaker CV and Disclosure) | 40 days prior |
| OCPE | Create Activity Description Form (ADF) in ACPE Webtool | 30 days prior |
| Planning Committee | Submit Activity Announcement (incl. additional promotional materials) for approval The announcement must be approved prior to dissemination or public posting; and included with ALL marketing and outreach efforts. | 21 days prior |
| Planning Committee | Submit final activity content (educational materials: slides, polls, questions, etc.) Submit final activity evaluation, if applicable. - Failure to submit activity content may result in approval being withdrawn. - Speakers with potential conflicts or disclosures may be required to submit slides before activity approval. - For home study activities, it is recommended to submit activity content for approval prior to recording/production. | 14 days prior |
| OCPE | Send activity evaluation link to JP | 7 days prior |

## POST ACTIVITY

| Responsibility | Task | Due Date |
| --- | --- | --- |
| Planning Committee | Online activity evaluation sent to eligible participants | Post activity |
| Planning Committee | Submit LIVE attendance sheet/sign in | 7 days after activity date |
| Planning Committee | Submit HOME STUDY attendance sheet/sign in | Monthly |
| OCPE | Activity evaluations closed to participants | 10 days after activity date |
| OCPE | Credits uploaded to CPE webtool | No later than 60 days |
| OCPE | Activity evaluation summary emailed to JP, if applicable | No later than 60 days |

Deliverables should be submitted via email to continuinged@rx.umaryland.edu.